## Sheet0
Glasgow Queen Street Station Redevelopment webinar, 9 March 2021
Questions asked | Answers provided
How did your understanding of stakeholders evolve over time and how much did you know upfront? | The stakeholder engagement for the redevelopment of Queen Street started (2013/2014) well in advance of work beginning on site in 2017. At that stage, we sought to engage with an extensive group, particularly those identified as affected by or interested in our proposals, as we recognised taking a number of different views, opinions and needs into account was important as we shaped our plans for the redevelopment. This included passengers, the station/ScotRail, Glasgow City Council, people living within the immediate area, businesses, property owners, tenants, councillors and elected representatives, interest groups including our stakeholder forum and statutory consultees. During the construction stage, much of the focus concentrated on those most directly impacted upon by the daily delivery of the actual construction work (local businesses and residents, passengers including those with mobility challenges and sensory impairments, the station staff and Glasgow City Council).
did the covid pause result in a contractor claim or was it covered under force major? | There was a change control submitted for Covid costs - this is commercially sensitive information.
was there a stakeholder/comms conflict with Baffour who are very active with their community liaison vs the client comms role? | No, it was very much a collaboration between Network Rail and Balfour Beatty - where we worked collectively, including our stakeholder engagement/liaison.
Having stood outside queen street waiting on a taxi after a night out which many do was it advisable to make the frontage out of glass?!! | Unsure what the relevance of this question is - the frontage of the station comprises of toughened glass and there is no taxi rank directly outside the station front. BTP also has a dedicated resource at Queen Street.
I believe there was some initial delays in the expected time for receiving the TAWS application back versus when you had actually received it. Was there anything you did to still utilize that time between delay and approval to increase efficiency? | The Statutory Powers (TAWS) application to authorise the development of Glasgow Queen street Station took longer than was originally anticipated at the time of application submission. The additional time afforded to the project by this was put to use in a number of ways. Not all of the physical works required as part of Queen Street station redevelopment were contingent upon the TAWS order being granted. As certain works were not tied to the TAWS, such works could start in advance of the Order being granted. This included things like cable diversion, cable correlation, certain preparatory works such as clearance of vacant shop units, allowing the project to get a head start when approval was granted.
Hello Kim, Jon and Joe, I am a student of Msc project management, I joined this webinar to understand some practical knowledge related to railway projects. Joe mentioned that station and hotels were running simultaneously. I want to know about managing risks in such conditions. Appologies if its not relevant. | Weekly meetings were held with the Millennium Hotel to discuss work and identify any risks, which were managed by project team on site. Similar meetings were also held with the station staff on a daily basis and again, any risks were managed by the project team on site.
what is your best and effective method of dealing with conflict? Especially with internal stakeholders and suppliers? Thanks! | To engage around a table/Teams calls in order to provide a space where individuals felt they could air their feelings and to also compromise where possible.
Really interesting presentation. It sounds like good planning has resulted in a successful project. Apart from the unexpected situation which covid has brought, what has been your biggest challenge during the redevelopment ? | The biggest challenge outwith Covid-19 has been managing the public passing through the worksite each day.
What would you say was the single biggest factor in on the on time delivery of the programme of works? | Collaboration - All decisions were made on a best for project basis.
What would you say as a project you did differently to other rail station development programmes? | We did not do anything different from other station redevelopments in terms of the work - however, being based on site one hundred percent of the time and cohabiting with our contractor was a great help to all.
wow..95% recycled of 14kTon's. that's good going. Did you get money back on it or break even on the cost?? | As discussed on Webinar this was cost neutral.
Would you incore costs for delivering late on the platforms? | Had we not re-opened the platforms on time following the extension work, Network Rail would have been penalised for this.
Did anything go wrong in delivering the platforms? What and how did you resolve the problems that were risking the delay of platform deliveries? What was the number one risk? | Yes, there were a few issues during the platforms 2/3 blockade. The biggest risk was during the drilling of baseplates, as we encountered vertical reinforcement which caused delay and we had to expedite resources to assist and ensure we stayed on programme. We kept a register of events on a daily basis and this allowed us to complete lessons learned in advance of the next blockade for platforms 4 and 5.
In your shut down, did you incure additional costs to bring the contractors back? Taking kit out and back in cost a lot of money. How much do you think additional costs added to the delay? | We had a two week period of remobilisation and we allowed for this in our rebaselined programme.
Did insurance cover for CV19 over costs? | The Covid-19 costs were recovered from Transport Scotland via a project change request.
Other than the completion of the project was there a benefits realisation strategy for the project? If so, was it successful? | The Benefits Realisation Strategy was developed in the early GRIP stages. The redevelopment of Queen Street was essential to the overall objective of the Edinburgh Glasgow Improvement Programme (EGIP), a comprehensive package of improvements including electrification of the main line between Edinburgh and Glasgow via Falkirk High. Although work at Queen Street represents the final element of EGIP, it was critical to the strategic delivery of the wider outputs and the key benefit of introducing longer, greener electric trains between the two cities. The platform extensions achieved this outcome.
Many thanks for sharing your experiences. Quick questions if I may, a) The time impact of the Covid 19 is over 5 months, but what about the cost impact. I am aware that the specific contract values have been omitted due to some sensitive nature, but I would like to see only the cost impacts? b) Did you come across any contamination requiring remediation? Example asbestos or any residual oils or chemicals? | a) Covid-19 costs were significant, but this is commercially sensitive information b) We had a specialist sub-contractor who carried out removal of asbestos on behalf of the principal contractor.
Joe. You mentioned regular use of lessons learned. Does Network Rail have a depository for those lessons/experiences can be used be other Network Rail projects? | The Programme Management Discipline has a central depository for lessons learned, which can be accessed by all.
are there any aspects of working practice changes brought about by Covid restrictions that you would retain for future project working? | Going forward, I believe we will be living with Covid-19 for some time and the processes we have in place now will become business as usual.